## IITKMS_TIMELINE
ID | ✎ |  | Editable User Area |  |  | ✎ | Progress Bar | Days | Work Days | Summary Task | Parent | Children | Options | Backup | 2025 | [27 empty] | 2025 | [30 empty] | 2025 | [29 empty] | 2025 | [30 empty] | 2025 | [29 empty] | 2025 | [30 empty] | 2025 | [30 empty] | 2025 | [29 empty] | 2025 | [30 empty] | 2025 | [29 empty] | 2025 | [30 empty] | 2026 | [30 empty] | 2026 | [27 empty] | 2026 | [30 empty] | 2026 | [29 empty] | 2026 | [30 empty] | 2026 | [29 empty] | 2026 | [30 empty] | 2026 | [30 empty] | 2026 | [29 empty] | 2026 | [30 empty] | 2026 | [29 empty] | 2026 | [30 empty] | 2027 | [30 empty] | 2027 | [27 empty] | 2027 | [30 empty] | 2027 | [29 empty] | 2025 | [9 empty] | 2025 | [12 empty] | 2025 | [12 empty] | 2025 | [12 empty] | 2026 | [12 empty] | 2026 | [12 empty] | 2026 | [12 empty] | 2026 | [12 empty] | 2027 | [12 empty] | 2027 | [5 empty] | 2025 |  |  | 2025 |  |  | 2025 |  |  | 2026 |  |  | 2026 |  |  | 2026 |  |  | 2026 |  |  | 2027 |  |  | 2027
[15 empty] | February | [27 empty] | March | [30 empty] | April | [29 empty] | May | [30 empty] | June | [29 empty] | July | [30 empty] | August | [30 empty] | September | [29 empty] | October | [30 empty] | November | [29 empty] | December | [30 empty] | January | [30 empty] | February | [27 empty] | March | [30 empty] | April | [29 empty] | May | [30 empty] | June | [29 empty] | July | [30 empty] | August | [30 empty] | September | [29 empty] | October | [30 empty] | November | [29 empty] | December | [30 empty] | January | [30 empty] | February | [27 empty] | March | [30 empty] | April | [29 empty] | January | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  |  | April |  |  |  | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March | April
| Work Breakdown Structure | Start | End | Person | Progress | Dependency | [8 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
[15 empty] | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M | M
1 | SUPRA SAE Procurement |  | 2025-03-12 |  |  |  |  | 1 | 1 |  |  |  | ["Activate PRO features"] | ["1","SUPRA SAE Procurement","",1741737600000,"","","","","","","","","","[\"Activate PRO features\"]","","",""]
2 | Design Phase 1 | 2025-03-01 | 2025-05-31 |  |  |  |  | 92 | 65 |  |  |  | ["Activate PRO features"] | ["2","Design Phase 1",1740787200000,1748649600000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: March 1 S to May 31 S; February 9 M to May 22 M
3 | Ideation (next tenure) | 2025-03-01 | 2025-03-18 |  |  |  |  | 18 | 12 |  |  |  | ["Activate PRO features"] | ["3","Ideation (next tenure)",1740787200000,1742256000000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: March 1 S to March 18 T; February 9 M to March 12 M
4 | Aligning of goals and classification | 2025-03-18 | 2025-03-24 |  |  |  |  | 7 | 5 |  |  |  | ["Activate PRO features"] | ["4","Aligning of goals and classification",1742256000000,1742774400000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: March 18 T to March 24 M; March 12 M to March 13 M
5 | Procurement List ('26) | 2025-03-24 | 2025-03-29 |  |  |  |  | 6 | 5 |  |  |  | ["Activate PRO features"] | ["5","Procurement List ('26)",1742774400000,1743206400000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: March 24 M to March 29 S; March 13 M
6 | Procurement Classification | 2025-03-29 | 2025-03-31 |  |  |  |  | 3 | 1 |  |  |  | ["Activate PRO features"] | ["6","Procurement Classification",1743206400000,1743379200000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: March 29 S to March 31 M; March 13 M to March 14 M
7 | Work on E13 | 2025-03-12 | 2025-03-22 |  |  |  |  | 11 | 8 |  |  |  | ["Activate PRO features"] | ["7","Work on E13",1741737600000,1742601600000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: March 12 W to March 22 S; March 11 M to March 12 M
8 | P1 Procurement | 2025-04-01 | 2025-04-14 |  |  |  |  | 14 | 10 |  |  |  | ["Activate PRO features"] | ["8","P1 Procurement",1743465600000,1744588800000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: April 1 T to April 14 M; March 14 M to April 16 M
9 | Cell and segment selection | 2025-04-08 | 2025-04-12 |  |  |  |  | 5 | 4 |  |  |  | ["Activate PRO features"] | ["9","Cell and segment selection",1744070400000,1744416000000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: April 8 T to April 12 S; April 15 M
10 | Accumulator cooling | 2025-04-12 | 2025-04-16 |  |  |  |  | 5 | 3 |  |  |  | ["Activate PRO features"] | ["10","Accumulator cooling",1744416000000,1744761600000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: April 12 S to April 16 W; April 15 M to April 16 M
11 | VD points 1st iter | 2025-03-15 | 2025-04-15 |  |  |  |  | 32 | 22 |  |  |  | ["Activate PRO features"] | ["11","VD points 1st iter",1741996800000,1744675200000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: March 15 S to April 15 T; March 11 M to April 16 M
12 | Chassis design 1st iter | 2025-05-07 | 2025-05-20 |  |  |  |  | 14 | 10 |  |  |  | ["Activate PRO features"] | ["12","Chassis design 1st iter",1746576000000,1747699200000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: May 7 W to May 20 T; May 19 M to May 21 M
13 | BWA (Brake Pedal + rack Design) | 2025-04-15 | 2025-04-24 |  |  |  |  | 10 | 8 |  |  |  | ["Activate PRO features"] | ["13","BWA (Brake Pedal + rack Design)",1744675200000,1745452800000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: April 15 T to April 24 T; April 16 M to April 17 M
14 | Electrical circuit diagram | 2025-05-12 | 2025-05-24 |  |  |  |  | 13 | 10 |  |  |  | ["Activate PRO features"] | ["14","Electrical circuit diagram",1747008000000,1748044800000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: May 12 M to May 24 S; May 20 M to May 21 M
15 | PCB box (E13) | 2025-05-24 | 2025-06-01 |  |  |  |  | 9 | 5 |  |  |  | ["Activate PRO features"] | ["15","PCB box (E13)",1748044800000,1748736000000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: May 24 S to June 1 S; May 21 M to May 22 M
16 | Wheel assembly design | 2025-05-25 | 2025-06-01 |  |  |  |  | 8 | 5 |  |  |  | ["Activate PRO features"] | ["16","Wheel assembly design",1748131200000,1748736000000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: May 25 S to June 1 S; May 21 M to May 22 M
17 | Design Phase 1 (REVIEW) | 2025-06-01 | 2025-06-03 |  |  |  |  | 3 | 2 |  |  |  | ["Activate PRO features"] | ["17","Design Phase 1 (REVIEW)",1748736000000,1748908800000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: June 1 S to June 3 T; May 22 M to June 23 M
18 | Design Phase 2 alignment | 2025-06-03 | 2025-06-05 |  |  |  |  | 3 | 3 |  |  |  | ["Activate PRO features"] | ["18","Design Phase 2 alignment",1748908800000,1749081600000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: June 3 T to June 5 T; June 23 M
19 | Design Phase 2 | 2025-06-05 | 2025-08-31 |  |  |  |  | 88 | 62 |  |  |  | ["Activate PRO features"] | ["19","Design Phase 2",1749081600000,1756598400000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: June 5 T to August 31 S; June 23 M to August 35 M
20 | Suspension and Steering CAD | 2025-06-05 | 2025-06-10 |  |  |  |  | 6 | 4 |  |  |  | ["Activate PRO features"] | ["20","Suspension and Steering CAD",1749081600000,1749513600000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: June 5 T to June 10 T; June 23 M to June 24 M
21 | Chassis CAD integration | 2025-06-01 | 2025-06-10 |  |  |  |  | 10 | 7 |  |  |  | ["Activate PRO features"] | ["21","Chassis CAD integration",1748736000000,1749513600000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: June 1 S to June 10 T; May 22 M to June 24 M
22 | BWA innovation | 2025-06-10 | 2025-06-18 |  |  |  |  | 9 | 7 |  |  |  | ["Activate PRO features"] | ["22","BWA innovation",1749513600000,1750204800000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: June 10 T to June 18 W; June 24 M to June 25 M
23 | Electrical wiring +PCB box (CAD) | 2025-06-14 | 2025-06-21 |  |  |  |  | 8 | 5 |  |  |  | ["Activate PRO features"] | ["23","Electrical wiring +PCB box (CAD)",1749859200000,1750464000000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: June 14 S to June 21 S; June 24 M to June 25 M
24 | Aerodynamics (Design and RnD) | 2025-06-15 | 2025-07-02 |  |  |  |  | 18 | 13 |  |  |  | ["Activate PRO features"] | ["24","Aerodynamics (Design and RnD)",1749945600000,1751414400000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: June 15 S to July 2 W; June 24 M to June 27 M
25 | Consolidated results (Innovation) | 2025-07-02 | 2025-07-05 |  |  |  |  | 4 | 3 |  |  |  | ["Activate PRO features"] | ["25","Consolidated results (Innovation)",1751414400000,1751673600000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: July 2 W to July 5 S; June 27 M
26 | Procurement iteration | 2025-07-05 | 2025-07-08 |  |  |  |  | 4 | 2 |  |  |  | ["Activate PRO features"] | ["26","Procurement iteration",1751673600000,1751932800000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: July 5 S to July 8 T; June 27 M to July 28 M
27 | Procurement P2 and P3 | 2025-07-08 | 2025-07-14 |  |  |  |  | 7 | 5 |  |  |  | ["Activate PRO features"] | ["27","Procurement P2 and P3",1751932800000,1752451200000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: July 8 T to July 14 M; July 28 M to July 29 M
28 | PRE SUPRA SAE '25 | 2025-07-14 | 2025-08-10 |  |  |  |  | 28 | 20 |  |  |  | ["Activate PRO features"] | ["28","PRE SUPRA SAE '25",1752451200000,1754784000000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: July 14 M to August 10 S; July 29 M to August 32 M
29 | Suspension and Steering repair | 2025-07-14 | 2025-07-20 |  |  |  |  | 7 | 5 |  |  |  | ["Activate PRO features"] | ["29","Suspension and Steering repair",1752451200000,1752969600000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: July 14 M to July 20 S; July 29 M
30 | Electrical wiring + PCB (E13) | 2025-07-14 | 2025-07-20 |  |  |  |  | 7 | 5 |  |  |  | ["Activate PRO features"] | ["30","Electrical wiring + PCB (E13)",1752451200000,1752969600000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: July 14 M to July 20 S; July 29 M
31 | Powertrain (repair and assembly) | 2025-07-20 | 2025-07-23 |  |  |  |  | 4 | 3 |  |  |  | ["Activate PRO features"] | ["31","Powertrain (repair and assembly)",1752969600000,1753228800000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: July 20 S to July 23 W; July 29 M to July 30 M
32 | Assembly | 2025-07-23 | 2025-07-25 |  |  |  |  | 3 | 3 |  |  |  | ["Activate PRO features"] | ["32","Assembly",1753228800000,1753401600000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: July 23 W to July 25 F; July 30 M
33 | Testing | 2025-07-25 | 2025-08-05 |  |  |  |  | 12 | 8 |  |  |  | ["Activate PRO features"] | ["33","Testing",1753401600000,1754352000000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: July 25 F to August 5 T; July 30 M to August 32 M
34 | Packing / Logistics | 2025-08-05 | 2025-08-10 |  |  |  |  | 6 | 4 |  |  |  | ["Activate PRO features"] | ["34","Packing / Logistics",1754352000000,1754784000000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: August 5 T to August 10 S; August 32 M
35 | SUPRA SAE'25 Competition | 2025-08-10 | 2025-08-20 |  |  |  |  | 11 | 8 |  |  |  | ["Activate PRO features"] | ["35","SUPRA SAE'25 Competition",1754784000000,1755648000000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: August 10 S to August 20 W; August 32 M to August 34 M
36 | Final design iter (SUPRA learnings) | 2025-08-20 | 2025-08-30 |  |  |  |  | 11 | 8 |  |  |  | ["Activate PRO features"] | ["36","Final design iter (SUPRA learnings)",1755648000000,1756512000000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: August 20 W to August 30 S; August 34 M to August 35 M
37 | Powertrain Testing | 2025-09-01 | 2025-09-15 |  |  |  |  | 15 | 11 |  |  |  | ["Activate PRO features"] | ["37","Powertrain Testing",1756684800000,1757894400000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: September 1 M to September 15 M; September 36 M to September 38 M
38 | HV testing | 2025-08-10 | 2025-08-25 |  |  |  |  | 16 | 11 |  |  |  | ["Activate PRO features"] | ["38","HV testing",1754784000000,1756080000000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: August 10 S to August 25 M; August 32 M to August 35 M
39 | Complete CAD integration | 2025-08-23 | 2025-08-28 |  |  |  |  | 6 | 4 |  |  |  | ["Activate PRO features"] | ["39","Complete CAD integration",1755907200000,1756339200000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: August 23 S to August 28 T; August 34 M to August 35 M
40 | Technical Report Submission | 2025-08-28 | 2025-08-31 |  |  |  |  | 4 | 2 |  |  |  | ["Activate PRO features"] | ["40","Technical Report Submission",1756339200000,1756598400000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: August 28 T to August 31 S; August 35 M
41 | MANUFACTURING | 2025-09-01 | [5 empty] | 1 | 1 |  |  |  | ["Activate PRO features"] | ["41","MANUFACTURING",1756684800000,"","","","","","","","","","","[\"Activate PRO features\"]","","",""]
42 | Procurement P4 | 2025-09-01 | 2025-09-07 |  |  |  |  | 7 | 5 |  |  |  | ["Activate PRO features"] | ["42","Procurement P4",1756684800000,1757203200000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: September 1 M to September 7 S; September 36 M
43 | Chassis tube cutting and profiling | 2025-09-01 | 2025-09-14 |  |  |  |  | 14 | 10 |  |  |  | ["Activate PRO features"] | ["43","Chassis tube cutting and profiling",1756684800000,1757808000000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: September 1 M to September 14 S; September 36 M to September 37 M
44 | Chassis welding + jigs | 2025-09-07 | 2025-09-20 |  |  |  |  | 14 | 10 |  |  |  | ["Activate PRO features"] | ["44","Chassis welding + jigs",1757203200000,1758326400000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: September 7 S to September 20 S; September 36 M to September 38 M
45 | Aero devices design manufacturing | 2025-09-01 | 2025-09-14 |  |  |  |  | 14 | 10 |  |  |  | ["Activate PRO features"] | ["45","Aero devices design manufacturing",1756684800000,1757808000000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: September 1 M to September 14 S; September 36 M to September 37 M
46 | Suspension arms + steering mounts | 2025-10-02 | 2025-10-08 |  |  |  |  | 7 | 5 |  |  |  | ["Activate PRO features"] | ["46","Suspension arms + steering mounts",1759363200000,1759881600000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: October 2 T to October 8 W; September 40 M to October 41 M
47 | Accumulator welding | 2025-10-04 | 2025-10-11 |  |  |  |  | 8 | 5 |  |  |  | ["Activate PRO features"] | ["47","Accumulator welding",1759536000000,1760140800000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: October 4 S to October 11 S; September 40 M to October 41 M
48 | Powertrain integration | 2025-10-11 | 2025-10-17 |  |  |  |  | 7 | 5 |  |  |  | ["Activate PRO features"] | ["48","Powertrain integration",1760140800000,1760659200000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: October 11 S to October 17 F; October 41 M to October 42 M
49 | Accumulator completion | 2025-10-12 | 2025-10-20 |  |  |  |  | 9 | 6 |  |  |  | ["Activate PRO features"] | ["49","Accumulator completion",1760227200000,1760918400000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: October 12 S to October 20 M; October 41 M to October 43 M
50 | Suspension and steering assembly | 2025-10-20 | 2025-10-28 |  |  |  |  | 9 | 7 |  |  |  | ["Activate PRO features"] | ["50","Suspension and steering assembly",1760918400000,1761609600000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: October 20 M to October 28 T; October 43 M to October 44 M
51 | BWA assembly | 2025-10-28 | 2025-11-05 |  |  |  |  | 9 | 7 |  |  |  | ["Activate PRO features"] | ["51","BWA assembly",1761609600000,1762300800000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: October 28 T to November 5 W; October 44 M to November 45 M
52 | Bodyworks + Aero devices supports | 2025-11-05 | 2025-11-15 |  |  |  |  | 11 | 8 |  |  |  | ["Activate PRO features"] | ["52","Bodyworks + Aero devices supports",1762300800000,1763164800000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: November 5 W to November 15 S; November 45 M to November 46 M
53 | LV box + wiring | 2025-10-05 | 2025-11-05 |  |  |  |  | 32 | 23 |  |  |  | ["Activate PRO features"] | ["53","LV box + wiring",1759622400000,1762300800000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: October 5 S to November 5 W; September 40 M to November 45 M
54 | Electrical integration | 2025-11-05 | 2025-11-15 |  |  |  |  | 11 | 8 |  |  |  | ["Activate PRO features"] | ["54","Electrical integration",1762300800000,1763164800000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: November 5 W to November 15 S; November 45 M to November 46 M
55 | Powertrain + HV motor control | 2025-12-01 | 2025-12-15 |  |  |  |  | 15 | 11 |  |  |  | ["Activate PRO features"] | ["55","Powertrain + HV motor control",1764547200000,1765756800000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: December 1 M to December 15 M; December 49 M to December 51 M
56 | Circuit integration | 2025-12-15 | 2025-12-25 |  |  |  |  | 11 | 9 |  |  |  | ["Activate PRO features"] | ["56","Circuit integration",1765756800000,1766620800000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: December 15 M to December 25 T; December 51 M to December 52 M
57 | TI inspection | 2025-12-25 | 2025-12-28 |  |  |  |  | 4 | 2 |  |  |  | ["Activate PRO features"] | ["57","TI inspection",1766620800000,1766880000000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: December 25 T to December 28 S; December 52 M
58 | Changelog | 2025-12-28 | 2025-12-31 |  |  |  |  | 4 | 3 |  |  |  | ["Activate PRO features"] | ["58","Changelog",1766880000000,1767139200000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: December 28 S to December 31 W; December 52 M to December 1 M
59 | Assembly | 2026-01-01 | 2026-01-10 |  |  |  |  | 10 | 7 |  |  |  | ["Activate PRO features"] | ["59","Assembly",1767225600000,1768003200000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: January 1 T to January 10 S; December 1 M to January 2 M
60 | FS quiz | 2026-01-21 | 2026-01-31 |  |  |  |  | 11 | 8 |  |  |  | ["Activate PRO features"] | ["60","FS quiz",1768953600000,1769817600000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: January 21 W to January 31 S; January 4 M to January 5 M
61 | Final Assembly | 2026-01-14 | 2026-01-21 |  |  |  |  | 8 | 6 |  |  |  | ["Activate PRO features"] | ["61","Final Assembly",1768348800000,1768953600000,"","","","","","","","","","[\"Activate PRO features\"]","","",""] | bar: January 14 W to January 21 W; January 3 M to January 4 M
62 | TESTING | 2026-01-21 | [5 empty] | 1 | 1 |  |  |  | ["Activate PRO features"] | ["62","TESTING",1768953600000,"","","","","","","","","","","[\"Activate PRO features\"]","","",""]

## Please note
Date and time [GMT/UTC] | Message
2025 Feb 11, 12:31 [GMT/UTC] | Start date of task is after end date of task. Corresponding row: 67 The changes are going to be revoked.